## Project Tracking
NYS 21st CCLC Data Management Activity Log | [7 empty] | STATUS KEY | PRIORITY KEY
[8 empty] | On Hold | Low
DATA MANAGER(S): | [5 empty] | SCHOOL YEAR: 2023-2024 (Round 8, Yr. 2) |  | In Progress | High
Grant Project # |  | Sites: | [5 empty] | Complete
Data Management Task
TASK / Issue | DEADLINE/ SCHEDULE | DESCRIPTION | PRIORITY | START DATE | COMPLETION DATE | ASSIGNEE | STATUS | NOTES
Adapted from LPB Associates, with permission.

## Sample Project Tracking
Sample Activity Log | [6 empty] | Smartsheet Tip ➜ |  | STATUS KEY | PRIORITY KEY
[9 empty] | On Hold | Low
|  | DATA MANAGER |  |  | Shirley Chisholm |  | SCHOOL YEAR: 2022-23 |  | In Progress | High
|  | Grant Project # | 9000 |  | Sites: PS 123 |  |  |  | Complete
Data Task
TASK / Issue | DEADLINE/ SCHEDULE | DESCRIPTION | PRIORITY | START DATE | COMPLETION DATE | ASSIGNEE | STATUS | NOTES
EZReports Data Check |  | Check EZReports 21APR data. Activities and Staffing are missing | High | 2022-11-10 |  |  | In Progress | Emailed data entry person with the dates missing attendance to advise/complete
Data report for students enrolled | Monthly | Ran student hours report for PS 123 | Low | 2022-11-02 | 2022-11-03 |  | Complete | Shared report with site coordinators to ensure program is on track to meet target
Teacher Surveys |  | Created a template for site to capture data for teacher survey information | High | 2022-11-01 |  |  | On Hold | Will share template at the next planning meeting to get feedback and tweak accordingly
EOY Grades | Aug. 2023 | Obtain grades from district and enter into GPA Calculators | High | 2023-07-25 |  |  | In Progress | Completed calculators must be uploaded to EZReports by 8/31